## Slide 1
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017
PAT MEETING

## Slide 2
PAT MEETING
AGENDA
Introduction - Participants
Construction Progress Update – Turner Construction
General Questions
Remaining PAT Meetings Schedule for 2017
AGENDA
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017

## Slide 3
PAT MEETING
PARTICIPANTS
Eric Ford, Project Manager, HISD Facilities Design
Linda McClure, Project Manager, Turner Construction Company
Cándido Lizárraga , Project Engineer, Turner Construction Company
Luke Hiller , Assistant Engineer, Turner Construction Company
Wardell Ross Jr., Project Manager/Architect, Moody Nolan
Jonathan Mitchell., Construction Administrator, Moody Nolan
INTRODUCTIONS
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017

## Slide 4
PAT MEETING
Construction Progress Update
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017

## Slide 5
PAT MEETING
CONSTRUCTION PROGRESS SCHEDULE
CONSTRUCTION PROGRESS UPDATE
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017

## Slide 6: TURNER SAFETY & COMMUNITY
Turner is working to maintain a safe jobsite for the community and the workers
  Complete site perimeter fencing with lockable gates including signage to ensure authorized entry only.
  On site cameras with 24 hour monitoring to alert us when someone has entered the site without authorization.
  Full time on-site safety manager to ensure construction processes are safe and to improve worker safety.
  Weekly site weeks with the Yates students to monitor and record construction progress.

## Slide 7
PAT MEETING
CONSTRUCTION PROGRESS UPDATE
Building Pad and Piers have been completed.
Mockup panels are erected & painted, metal panels are up, storefront/window is installed.
Temporary metal panels are installed at building B & building A Separation.
Slab on Grade and forming/pouring of the tilt wall panels has begun, Area D & C are complete. U/G Plumbing/Electrical is moving ahead of this activity by Area and will be complete by 2/13/17.
Site utilities have been completed to the extent they can until Summer 2017.
BIM Coordination is 95% complete, working through clashes and resolutions.
Lifting or “tilting” the panels has begun on 2/2/17 in area D.
Steel Erection will follow the lifting of the panels.
CONSTRUCTION PROGRESS UPDATE
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017

## Slide 8
PAT MEETING
CONSTRUCTION PROGRESS UPDATE
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017
Building Exterior Mockup

## Slide 9
PAT MEETING
CONSTRUCTION PROGRESS UPDATE
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017
Building Pad and drilling piers.

## Slide 10
PAT MEETING
CONSTRUCTION PROGRESS UPDATE
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017
Tilt Wall Panel Erections

## Slide 11
PAT MEETING
CONSTRUCTION PROGRESS UPDATE
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017
Tilt Wall Panel Erections & Slab Pours

## Slide 12
PAT MEETING
CONSTRUCTION PROGRESS UPDATE
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017
Steel Joists Delivery

## Slide 13
PAT MEETING
CONSTRUCTION PROGRESS UPDATE
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017
Lint Trap – 9,500 #’s

## Slide 14
PAT MEETING
SCHEDULE FOR 2017
February 16, 2017 – Construction Progress Update
May 18, 2017 – Construction Progress Update
September 21, 2017 – Construction Progress Update
December 14, 2017 – Construction Progress Update
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017

## Slide 15
PAT MEETING
Questions
HISD JACK YATES HIGH SCHOOL
PAT MEETING
February 16, 2017